Bid to development of the project:

Panel Editor v. 2.0

Written by:

Dmitry Menshikov,

Project leader

# Table of contents

Table of contents	2

The description of the project development	3

1. Comments to principles of the project development	3

1.1. Development environment	3

1.2. Object –oriented structure	3

1.3. User interface	3

1.4. Supplementary	3

2. Steps of the project development	4

3. Payment procedure	4

4. Delivery items	4

Project estimation	4

# The description of the project development

## 1. Comments to principles of the project development

Below we suggest some principles, according to which your project will be developed. Some words that we must say before bid starts. All you can read further is not a dogma. We can discuss any part of the bid and change it as you like. But this is our vision of your project, and it would be better if all our suggestions suited you at once. Let's begin.

### Development environment

We suggest development of your application using MSVC++. It will help us to create a small-size and fast application. Presumably the compiled size will be within the range of 0,8 - 1,5 MB. And since C++ is a low-level language, the program protection system will be more effective than the current one. The application will be constructed according to object-oriented approach. We plan to use Microsoft ATL library for building objects, so final application will be capable of using VBA as a control center.

### 1.2. Object –oriented structure

We plan to create an object-oriented application. Objects can be grouped on assignment, but the main object is Panel Editor Application. The application consists of projects that represent electrical circuits. A project (i.e. circuit) consists of objects set described by you. Flexible object structure will eliminate the necessity to add new objects. The project structure will be flexible too. This means that you can create a new type of an electrical object (with VB, for example) and attach it to Panel Editor Application. Of course, this might be not quite easy, since you will have to implement a set of interfaces: drawing, electric properties, connectivity properties and so on. But this is possible, because we create dynamical objects. I.e. application will only know the set of electrical rules, and objects will act as electric devices that can consume power, conduct / transform / switch electrical current. Many checks will be performed on the fly. For example, if you overload a transformer, it will detect this fact and start blinking.

This is very expansible architecture. The only limitations are electrical rules that are present in the program. For example, you don't need to consider the capacity that may be present between two conductors (as it is on higher frequency). Moreover, we plan to select standard OLE storage for the project file, so, there will be no problems with embedding of objects (pictures, tables or drawings from other applications).

### 1.3. User interface

We suggest implementation of MDI graphical application that enables a user to create circuits visually, set properties (as in VB) and perform some checks. The ability to print circuits and generated reports will be also provided. Namely, the upper part of the application window will have standard menu and a toolbar. The status line will be at the bottom. Left part of project window will contain elements bar (as in Visio). Users can select and customize items of available elements list. For example, from element "electric bulb" one can create 100 W bulbs and 80 W bulbs. Main part of the project window will be the "Project area" - the place, where a user can create circuits by dragging elements from the elements bar and connecting them with conductors. Of course users can perform copy / paste operations. The properties window will be also provided as requested.

### 1.4. Supplementary

All your specifications will be implemented. To change the project file format we import logical structure from the previous project file (Jet database). All types of objects are also included in estimation. Panel editor will have installation system and advanced protective system. You may provide us with key creation algorithm, or we can implement our own. That's all at this point. Docs will contain about 20 A4-pages, and help will be about 40 html pages.

## 2. Steps of the project development

Total time of the project development is 2-3 months. Steps with their detailed descriptions are below.

- Basic structure implementation. Duration 2-3 weeks. We develop basic program structure and start coding.

- Prototype creation. Duration 2–3 weeks. At the end of this step we will have the prototype of the application ready, that is, basic functionalities (UI, project creation and editing) will be implemented. No analysis implemented. Exe file and code delivery.

- Beta 1 version. Duration 3-4 weeks. Fully functional version will be ready. Exe file delivery.

- Testing. Duration 1-2 weeks. During this time we test the application and accept your corrections. Exe file delivery.

- Final. Duration 2 weeks. Commercial high-quality application is ready. We prepare docs and help. Exe, code and docs delivery.

Total time of the project development may vary within 30% range. We will send you progress information weekly.

## 3. Payment procedure

We ask you to pay 1/3 after prototype creation, 1/3 after Beta 1 version, and 1/3 at final.  We are willing to create high-quality applications with low price (for given application functionality), so we ask you to permit us to give references that our programmer group has developed this project. Of course, copyright will belong to you. Once more about the price. It is not high since we are interested in this application development. We really like it!

## 4. Delivery items

- Binary files, ready for work (with installer);

- Source code  (all right for this code will belong to you);

- Source code documentation (in CHM format);

- Help file (in CHM format);

- Documentation (in PDF format).

# Project estimation

Here (Bid.xls) you will find precise project cost estimation. If we start development of this project, bid.xls will be used as a progress indicator (we will fill complete fields).